## Status
Deliverable | Date | Status (%)
A. Functional OpenMSE bag limit extension | 1st April 2023 | 100
B. Report documenting application to California Halibut | 1st Feb 2024 | 100
C. Report documenting application to second species | 1st April 2024 | 100
D. Draft Report | 1st May 2024 | 50
E. Final Report | 1st June 2024 | 10

## Tasks
Task | Status (%)
A. Examine and analyze the CDFW recreational catch data for California halibut and one other case-study to calculate probability of catching or exceeding the bag limit at a given stock size. | 100
B. Develop and describe the mathematical model used to calculate the impact of bag limits on the fishery dynamics, accounting for discard mortality and individual and boat bag limits and add to the openMSE framework as a management option that can be used in combination with other existing management options (e.g., TAC, TAE, etc.). | 100
C. Apply the bag limit feature to California halibut and one other case-study (e.g., groundfish species) identified by CDFW collaborators. | 100
D. Incorporate feedback from CDFW and other collaborators on technical documents and produce final project report. | 50
E. Provide co-authorship support for drafting CDFW scientists-led manuscript describing the methods and results of the application to the case-studies. | 0

## ATD
Priority | To Do
1 | Identify appropriate management levers (MPs) to test and also robustness / sensitivity operating models for each species.
2 | Finalize analyses and begin drafting peer-reviewed paper.
2 | Update CaliBL github repo and help documentation